## Project Charter
Project Charter
GENERAL PROJECT INFORMATION | CHARTER DATE: 19 September 2025
PROJECT NAME | AI-Powered Fraud Call Detection for SSN & Immigration Scams
PROJECT SPONSOR | Consumer Protection Agency / Telecom Provider Partner
PROJECT MANAGER | Team Lead
EXPECTED START DATE | 2025-10-01
EXPECTED COMPLETION DATE | 2026-06-30
PROJECT DETAILS
PROJECT DESCRIPTION | Develop an AI-based fraud call detection system that uses a mobile app and cloud backend to analyze audio streams in real-time with speech recognition, NLP, and anomaly detection. The system will deliver instant fraud alerts, protect vulnerable users, and ensure secure, scalable, and privacy-compliant deployment.
KEY REQUIREMENTS | Mobile app with caller ID verification and fraud detection MVP Real-time audio stream analysis using AI/ML models Backend API development for fraud detection services Secure data handling with encryption and privacy preservation Integration with telecom networks and mobile operating systems Multi-language support (Phase 2) Expansion to text, email, and social media scam detection (future phases)
EXPECTED BENEFITS | Minimize the financial impact of scam phone calls (approx. $43B yearly in the US) Shield at-risk and vulnerable populations against identity theft and financial fraud Demonstrate end-to-end software engineering (i.e., frontend, backend, cloud, AI Integration) Facilitate monetization via subscription, enterprise, and government contracts Aid compliance enforcement with increasing scam-reducing standards
ESTIMATED COST & RESOURCES | $500K–$750K initial development; requires mobile developers, backend engineers, AI/ML engineers, data engineers, security specialists, and QA resources.
ESTIMATED MILESTONES | Mobile app prototype with caller ID: Nov 2025 Backend APIs and cloud infrastructure setup: Dec 2025 Real-time audio streaming pipeline: Jan 2026 AI/NLP model integration: Feb 2026 Security hardening and privacy compliance: Mar 2026 Beta release with English support: May 2026 Final release with multi-language support: Jun 2026
PROJECT TEAM (RESOURCES) | Project Sponsor: Consumer Protection Agency / Telecom Partner Project Manager: Team Lead Mobile Developers: 2 Backend Engineers: 2 AI/ML Engineers: 3 Data Engineer: 1 Security Engineer: 1 QA/Test Engineer: 1 Telecom Integration SME: 1
STAKEHOLDERS (IMPACTED) | Telecom providers (network integration) Government fraud prevention agencies End users (individual subscribers) Financial institutions (fraud monitoring and alerts)
OVERALL PROJECT RISK | Operating system restrictions on call recording (Medium chance of occurrence, High severity of impact) Breach of data privacy (Medium chance of occurrence, High severity of impact) Delays in system integration with telecommunications providers (High chance of occurrence, Medium severity of impact) High false positive detections resulting in diminished user trust (Medium chance of occurrence, Medium severity of impact) Latency issues in detecting fraudulent calls in real-time (Medium likelihood, Medium severity of impact)
PROJECT EXIT CRITERIA | MVP identifies over 80% of scam calls while maintaining a false positive rate below 10% Secure back-end deployment with 99.9% uptime Scope of integration with a minimum of one telecom provider System usage of a minimum of 5,000 pilot users Adherence to regulatory standards (GDPR/CCPA, telecom guidelines)