## Weekly Project Gantt Chart
[17 empty] | 2025 | [11 empty] | 2026 | [13 empty] | 2026 | [12 empty] | 2026 | [12 empty] | 2026 | [11 empty] | 2027 | [13 empty] | 2027 | [12 empty] | 2027
| Project Start Date: | 2025-10-01 | [5 empty] | 2025-09-15 |  |  |  | 2025-10-13 |  |  |  |  | 2025-11-17 |  |  |  | 2025-12-15 |  |  |  | 2026-01-12 |  |  |  | 2026-02-09 |  |  |  |  | 2026-03-16 |  |  |  | 2026-04-13 |  |  |  |  | 2026-05-18 |  |  |  | 2026-06-15 |  |  |  | 2026-07-13 |  |  |  |  | 2026-08-17 |  |  |  | 2026-09-14 |  |  |  | 2026-10-12 |  |  |  |  | 2026-11-16 |  |  |  | 2026-12-14 |  |  |  | 2027-01-11 |  |  |  | 2027-02-08 |  |  |  |  | 2027-03-15 |  |  |  | 2027-04-12 |  |  |  |  | 2027-05-17 |  |  |  | 2027-06-14 |  |  |  | 2027-07-12 |  |  |  |  | 2027-08-16
| Project Name: | AI-Powered Fraud Call Detection (SSN & Immigration Scams) |  |  |  |  | Week Starting: | time axis 2025-09-08 to 2027-08-30
# | Activity | Assigned To | Start | End | Days | Status | % Done
1 | Project Kick-off & Team Alignment | Krisha, Riya, Hemín | 2025-10-01 | 2025-10-03 | 3 | Complete | 100% | bar: 2025-09-29
2 | Caller ID Verification Setup | Riya | 2025-10-04 | 2025-10-17 | 14 | Not started | 0% | bar: 2025-10-13
3 | Fraud Detection Rule Design | Krisha | 2025-10-18 | 2025-10-31 | 14 | Not started | 0% | bar: 2025-10-27
4 | Dataset Collection & Preprocessing | Hemin | 2025-11-01 | 2025-11-21 | 21 | Not started | 0% | bar: 2025-11-17
5 | Prototype (Mobile App) | Krisha & Hemín | 2025-11-22 | 2025-12-15 | 24 | Not started | 0% | bar: 2025-12-15
6 | Train ML Model for Scam Detection | Riya | 2025-12-16 | 2026-01-15 | 31 | Not started | 0% | bar: 2026-01-12
7 | Validate Model with Test Data | Hemin | 2026-01-16 | 2026-01-30 | 15 | Not started | 0% | bar: 2026-01-26
8 | Backend & App Integration | Krisha | 2026-02-01 | 2026-02-20 | 20 | Not started | 0% | bar: 2026-02-16
9 | User Alerts & Notifications | Riya & Hemin | 2026-02-21 | 2026-03-10 | 18 | Not started | 0% | bar: 2026-03-09
10 | Beta Testing with Telecom Partners | Hemin | 2026-03-11 | 2026-04-15 | 36 | Not started | 0% | bar: 2026-04-13
11 | Reporting & Analytics Features | Krisha | 2026-04-16 | 2026-05-15 | 30 | Not started | 0% | bar: 2026-05-11
12 | Scaling & Deployment | Riya | 2026-05-16 | 2026-06-15 | 31 | Not started | 0% | bar: 2026-06-15
13 | Project Closure & Lessons Learned | Krisha, Riya, Hemin | 2026-06-16 | 2026-06-30 | 15 | Not started | 0% | bar: 2026-06-29
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Statuses
| Not started | ◄ Insert more rows to insert more statuses
In progress
Blocked
Complete
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))