## Labor Estimate
Labor Estimate (Unit: Hours)
| Project Name: | AI-Powered Fraud Call Detection for SSN & Immigration Scams |  |  |  |  | Total Hours Needed | 611
Unique ID | WBS Item | Project Leads | Planning Team | Designers | Developers | Testers | Security Team | Contractors | Customer Support | Total Labor Hours
1 | Release 1 – Mobile App Prototype & Caller ID Verification | 10 | 5 | 10 | 40 | 10 | 5 | 0 | 0 | 80
2 | Release 1 – Fraud Detection Rules & Model Setup | 8 | 5 | 8 | 45 | 10 | 6 | 0 | 0 | 82
3 | Release 2 – AI Integration & Model Training | 10 | 5 | 6 | 50 | 10 | 7 | 0 | 0 | 88
4 | Release 2 – Validation & Backend Integration | 8 | 4 | 6 | 40 | 10 | 5 | 0 | 0 | 73
5 | Release 2 – User Alerts & Notifications | 6 | 3 | 8 | 30 | 10 | 5 | 0 | 0 | 62
6 | Release 3 – Telecom API Integration Testing | 6 | 4 | 5 | 35 | 10 | 8 | 0 | 0 | 68
7 | Release 3 – Reporting & Analytics Dashboard | 6 | 3 | 6 | 30 | 8 | 5 | 0 | 0 | 58
8 | Release 3 – Scaling, Testing & Deployment | 8 | 5 | 5 | 35 | 10 | 7 | 0 | 0 | 70
9 | Project Management, Docs & Training | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 30
| TOTAL | 77 | 49 | 54 | 305 | 78 | 48 | 0 | 0 | 611
~ 700 with +/- 15% margin

## Labor Cost Calculation
Role / Function | Hours | $/hr (rate) | Cost ($) | Notes
Project Leads | 77 | 80 | 6 160 | Krisha (PM + coordination)
Planning Team | 49 | 70 | 3 430 | Release planning & tracking
Designers | 54 | 65 | 3 510 | UI/UX + fraud flow design
Developers | 305 | 75 | 22 875 | Core app + backend + ML
Testers | 78 | 60 | 4 680 | QA and validation testing
Security Team | 48 | 85 | 4 080 | Data & model security
Contractors | 0 | 70 | 0 | In-house team only
Customer Support | 0 | 50 | 0 | No live deployment support yet
Total Labor Cost | 611 h (≈ 700) | — | $44 735 ≈ $45 000 | —

## Budgetary Estimate
Budgetary Estimate (MVP)
Project Name: | AI-Powered Fraud Call Detection for SSN & Immigration Scams |  | Total Budget Needed | 39600
Unique ID | Budget Items | # of Units | Cost/Unit | Total Costs
| Labor (From previous sheet) | 700 | 50 | 35000
| Tools (Subscriptions, Servers, Software Tools, Test Tools) | 1 | 2000 | 2000
| Hardware (If part of your product) | 1 | 500 | 500
| Subcontractors / Vendors (If part of your product) | 1 | 500 | 500
| Overhead/G&A (Facility, Tax, HR, Utilities, Insurance, etc.) | 1 | 10% | 500
| Contingency Reserves (Held by Project Manager) | 0 | 10% | 1000
| Management Reserves (Held by Business) | 0 | 5% | 300
| Traing/Documentation/Support Readiness | 1 | 300 | 300
| Total |  |  | 39600
D