## RACI
RACI - Resource Assignment Matrix
|  | Project Name: | AI-Powered Fraud Call Detection for SSN & Immigration Scams |  |  |  |  | Project Manager: | Team 6
R - Responsible - who performs the task A - Accountable - who signs off C - Consulted - who provides expert judgement I - Who is kept informed
|  | Deliverables | Project Charter & Scope | Work Breakdown Structure | Project Schedule / Gantt | Budgetary Estimate | System Design & Architecture | AI Model Development | Mobile App Development | Backend & API Integration | Testing & Quality Assurance | Deployment & Scaling | Reporting & Analytics | Project Closure / Lessons Learned
NAME |  | PROJECT ROLE
Team 6 |  | Project Manager | A | A | A | A | C | I | I | C | C | A | A | A
Hemin Dhamelia |  | Deputy Project Manager | R | R | R | C | C | C | C | C | I | R | R | R
Krisha Lakhani |  | Functional Manager | C | C | I | C | R | C | I | I | I | I | I | C
Riya Patel |  | AI/ML Engineer | I | I | I | I | A | R | I | I | C | I | I | I
Jake Paul |  | Data Engineer | I | I | I | I | C | R | I | I | C | I | R | I | ◄ Insert more rows (for people) or columns (for tasks), and copy across an existing row or column to keep the formatting the same.
Sara Mac |  | Mobile Developer | I | I | I | I | I | I | R | C | C | R | I | I
John Cena |  | Backend Developer | I | I | I | I | C | I | C | R | C | R | I | I
Tom Holland |  | QA Engineer | I | I | I | I | I | C | C | C | R | C | C | I
Robert Downy |  | Security Specialist | I | I | I | I | C | C | C | C | C | R | I | I
Mark King |  | Telecom SME | bar: I to I
Lisa Orton |  | Government Liaison | I | I | I | I | I | I | I | I | I | I | C | R
| R | Responsible - who performs the task
| A | Accountable - who signs off | I: ◄ Insert new rows and letters to add abbreviations to the drop-down list
| C | Consulted - who provides expert judgement
| I | Informed - who is kept informed