## Test Cases
Project Communications Plan
|  | Project Name: | AI-Powered Fraud Call Detection for SSN & Immigration Scams |  | Date | 10-31-2025
Unique ID | Deliverable/Situation | Channel | Frequency | Upcoming Due Date | Owner | Internal Audience | External Audience | Purpose/ Agenda/ Content
1 | Project Kickoff | In-Person Meeting | One-Time | 2025-10-01 | Project Manager | Core Team | Project Sponsor – Consumer Protection Agency/Telecom Partner | Introduct the project, confirm project objectives, goals, and deliverables
2 | Project Proposal | Email + Teams presentation | One-Time | 2025-11-10 | Project Manager | Core team | Project Sponsor (Consumer Protection Agency), Telecom Partner | Seek approval on scope, budget, timeline
3 | Weekly Status | 30-min Teams stand-up + notes | Weekly (Fri) | Every Fri | Deputy Project Manager | All internal project members | None (internal report only) | Report progress, risks, next steps
4 | Customer Issue Escalation | Email/Teams | As needed (≤24h) | On occurrence | QA Lead | Project Manager, Security Specialist, Backend Developer | Telecom Partner Technical Contact | Log, triage, resolve customer-impacting issues
5 | Monthly Cost & Schedule Review | Review meeting + summary report | Monthly (EOM) | 2025-11-30 | Functional Manager | PM, Deputy PM, Data Engineer, Mobile Dev, QA | Project Sponsor, Finance Lead | Compare actuals vs plan; decide corrections
6 | Interpersonal conflict within team members | 1:1 mediation + summary email | As needed | On occurrence | Project Manager | Concerned team members | HR / Faculty Advisor (if unresolved) | Resolve conflict; agree actions and follow-up
7 | Product Launch Announcement | Press release + live demo webinar + email | One-Time | 2026-06-30 | Government Liaison | Entire project team | Consumer Protection Agency, Telecom Partner, End Users, Media | Announce launch, highlight features, access info