## Make or Buy Analysis
Make or Buy Analysis
|  | The Most Cost-Effective Option is: | Buy (Twilio Lookup API)
| Initial Costs | Ongoing Costs |  |  |  |  | TOTAL
Cost to Make | Initial | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Project costs (Backend + Security + Telecom SME) | 3000 | 0 | 0 | 0 | 0 | 0 | 3000
Developer labor for build (2 weeks) | 1200 | 0 | 0 | 0 | 0 | 0 | 1200
System Costs (Server hosting, ML pipeline) | 400 | 150 | 150 | 150 | 150 | 150 | 1150
Data labeling + model tuning | 300 | 100 | 100 | 100 | 100 | 100 | 800
Maintenance + bug fixes | 0 | 300 | 300 | 300 | 300 | 300 | 1500
Security updates + compliance | 0 | 150 | 150 | 150 | 150 | 150 | 750
TOTAL | 4900 | 700 | 700 | 700 | 700 | 700 | 8400
Cumulative Chart | 4900 | 5600 | 6300 | 7000 | 7700 | 8400
Cost to Buy | Initial | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Initial contract + onboarding | 1000 | 0 | 0 | 0 | 0 | 0 | 1000
API subscription + system access | 200 | 200 | 200 | 200 | 200 | 200 | 1200
Integration development | 250 | 0 | 0 | 0 | 0 | 0 | 250
Ongoing API usage fees | 0 | 350 | 450 | 500 | 550 | 600 | 2450 | ◀ Insert more rows to add more costs. Copy the formulas and formatting from an existing row from above.
Maintenance (Minor fixes) | 0 | 100 | 100 | 100 | 100 | 100 | 500 | ◀ Insert more columns to add more years (or weeks or months). Copy over an existing column to ensure the formulas carry over.
Security + regulatory compliance | 0 | 50 | 50 | 50 | 50 | 50 | 250
TOTAL | 1450 | 700 | 800 | 850 | 900 | 950 | 5650
Cumulative Chart | 1450 | 2150 | 2950 | 3800 | 4700 | 5650
x